CMMAP Team Meeting Breakout Group #4, July 31, 2008

Partnerships in Education and Diversity

Discussion Topic - How will we package and port the CMMAP Climate and Weather Teachers Workshop to other locations?

Overview of Agenda

- What is needed to successfully implement our CMMAP workshop?

- What are the possibilities for dissemination?

- Identify focus and priorities – Our Plan

Discussion and products

- What is needed to successfully implement our CMMAP workshop?  (sticky note process summarized)

  - Team Leadership

    - Trained or experienced team of 5 or more is needed

    - People who lead must know the material, be experienced with hands on components, and be enthusiastic

    - A climate scientist who is enthusiastic and credentialed

    - Organizational lead to facilitate transitions between activities and discussions

    - Graduate students should be trained and included with real roles to play in teaching

    - Classroom teacher to present materials and lead discussion about classroom integration

    - Person who is the key contact during pre-workshop planning, logistics planning, recruitment, and registration

    - Administrative support (Travel authorizations, invoicing, budget management, logistics, etc.)

  - Content and Pedagogy

    - Review, revise, and finalize syllabus and workshop time structure

    - Combination of lecture and activities

    - Model good, best practices in pedagogy

    - Follow the 5 E pedagogy for effective science teaching

    - Don’t let scientists misjudge their audience. Scientist-instructors must avoid using too much jargon and math which is too technical.

    - Rehearse, critique, and improve talks and activities in advance.

    - Practice delivery of hands-on activity and linking them seamlessly to content lectures and discussions

    - Include time for participants to network with each other to share ideas, encourage success, and provide mutual ongoing support

    - Maintain a safe environment to explore, learn, test ideas, fail, and learn from mistakes

    - Ensure that there is quick and easy access to resources during the workshop and for teachers when they return to their schools (web site). Develop and then post/share workshop props and slides. Add links to related Windows to the Universe content, interactives, and other resources.

    - Allow time to plan how the learning will be applied to classroom practice after teachers go home

    - Link content to state or national standards

    - Allow for some flexibility in the program to take advantage of teachable moments

    - Evaluation provided by a professional

  - University credit

    - Identify a division of continuing education or similar entity through which to offer workshop credit to teachers

    - Determine whether teachers or program will pay for the credit

  - Budget

    - Stipend - $1000 per teacher/participant for 5 days

    - Supplies - $250/teacher.

    - Assess CMMAP budget to see how it will be impacted by Ft. Collins expansion option or implementation at another site.

    - Determine what fundraising is needed, if any, and how to proceed.

  - Facilities and logistics

    - Classroom space with lecture and demo areas and tables for group hands-on activities

    - Prep space for LSOP last minute needs and receipt of materials when shipped to site.

    - Storage space for LSOP material, convenient for easy set up and clean up of equipment and materials each day

    - Demo equipment

    - Catering support for breaks at a minimum

    - A/V and I/T support

    - Convenient and affordable lodging for staff and participants

    - Catering for food and breaks or inexpensive restaurants immediately near by and per diem for teachers

  - Sustainability/Continuity

    - Create long term goals and plans

    - Work with partners who have an interest in ongoing teacher education and an established infrastructure to support it

    - Successful achievement in one remote location will help CMMAP to know what to look for in other locations

    - Explore AMS education programs for help and models

    - Partners must help on advertising the workshop

    - Generate “lasting” excitement

  - Encourage classroom implementation following workshop

    - Find ways to engage teachers’ long-term interest in the workshop and its outcomes so to promote its use in their own communities

    - Remove teachers from their home environment. This would increase the opportunity for increased “processing” time leading to classroom implementation

    - Recruit and train teaching/administrative staff for implementation in their districts

    - Plant the seeds of excitement and this will grow where the ground is good

  - Local partnership

    - Develop a good description of the workshop to be used for promotional purposes – a prospectus

    - Develop the schedule for the workshop and the planning timeline

    - Create a marketing timeline and registration process

    - Engage help from the local school districts so that you will know the science requirements in their schools

    - Leverage local school districts to recruit teachers

  - Local relevance

    - Identify teacher or teaching supervisor in a potential host city a hear or two in advance, have them attend a workshop so they can prepare to go home to plan an implementation and recruit teachers there

    - We are told that this is a compelling topic and that it is needed in their professional development

    - Hold a focus group in advance of a remote workshop to learn how to make the content most useful to teachers in the area

    - Recruit teachers from outside of CO who will come to train during our workshop and take the concept home with them

    - Teacher or district level curriculum director who will serve as a trainer of trainers when returned to home

  - Supplies for teachers

    - Make course easy to teach by providing them with the supplies they will need to do activities in their classrooms

    - Costs of supplies for teachers = $250

    - Build in time and staff support for purchasing and creating kits of the course equipment

    - Identify a small number of suppliers for materials and a close by as possible for “one stop shopping.”

- What are the possibilities for dissemination?

  - CMMAP workshop in other locations

    - Enthusiastic partners ensuring successful implementation

    - Potential for sustaining the workshop in future years

    - Identification and access to additional funding/staffing as needed

  - CMMAP workshop here with teachers from other regions

    - Customization of our workshop’s components that can be adapted to address the needs of others

- Our Plan

  - Plan a 2009 Ft Collins Workshop

    - With educators/scientists/graduate students strategically involved from other CMMAP institutions in other regions

    - Expectation that representatives from other regions will do some local kind of implementation at home

    - Weigh options for continuing to train local teachers, establishing a cap for best quality experiences, and costs of expansion.

  - January 2009 CMMAP Team meeting

    - Meet with strategic partners in NYC (Robert Pincus, Jay Fein,  Bill Rossow, Eric Tromeur)

    - Further clarification of needs and support for  broader and sustained outreach on west coast and through national organizations, e.g., Sally Ride Inst. (Richard Somerville and Tom Ackerman)

  - Write a white paper to serve as a prospectus describing the workshop and supporting fund raising efforts (Scott Denning and Brian Jones)